Progress Summary

Forensic Artefact Analysis of Cryptocurrency Wallet Applications on Android — status as of 18 August 2026

Note on this document: items below marked “self-reported” reflect what has been described in conversation and have not been independently verified (e.g. by inspecting the emulator, ethics portal, or reading notes directly). Treat this as a starting point to correct at the meeting, not a final record.

# 1. Timeline Reality Check

|  | Original plan (drafted ~5 July) | Actual, as of 18 August |
| --- | --- | --- |
| Days to submission | ~79 days (11 weeks) from plan start | 35 days (5 weeks) remaining |
| Module's own suggested pace | — | Guidance says Introduction & Literature Review proofreading should already be well underway by August |
| Introduction | Planned for weeks 7–9 | Drafted in full today |
| Methodology | Planned for weeks 7–9 | Drafted in full today |
| Literature Review | Planned for weeks 7–9 | Structured skeleton only — sources not yet added |
| Experimental phases (A0–A12) | Planned to run weeks 4–6 | Not yet started, per self-report |

Flag: The gap between the original plan's pacing and where things actually stand is the single most important thing to raise tomorrow. It doesn't mean the project is off track — Chapters 1 and 3 are further ahead than the original schedule assumed — but the 13-phase, 3-app experimental design needs a supervisor-agreed go/no-go on scope given 5 weeks remain.

# 2. What's Confirmed Done

## Literature review

- Reading in progress across Android forensics, cryptocurrency wallet architecture, Android storage/security, and evidential-value literature (self-reported; specific source count and coverage not yet detailed).

## Device and application setup

- Android Studio emulator selected as the test environment (self-reported).

- Wallet app categories agreed: EVM/Web3 (MetaMask Mobile candidate), multi-chain (Trust Wallet/Coinbase Wallet candidate), Bitcoin-focused (BlueWallet/Bitcoin Wallet candidate) — specific single apps per category not yet confirmed as locked.

- Rooted vs. non-rooted emulator image status not yet confirmed — needed for full-filesystem acquisition (RQ3).

## Ethics

- CURES ethics approval submitted (self-reported). Decision status (approved / pending / conditions) not yet confirmed — this is a hard gate per the module handbook: no data collection before approval, and the thesis cannot be marked without it on file.

## Thesis document

- Working LaTeX thesis built on Cranfield's official CUThesisTemplate2026 (APA7 Author-Date referencing).

- Chapter 1 (Introduction) drafted in full: background, research gap, aim, RQ1–RQ4, scope/boundaries, structure overview.

- Chapter 3 (Methodology) drafted in full: research design, wallet selection rationale, device/environment, the 13-phase action sequence, acquisition strategy, artefact taxonomy, evidential-value scoring framework, tools, ethics, and limitations.

- Chapter 2 (Literature Review) structured with seven themed sections and guidance notes for each — intentionally left without citations until real sources are read, to avoid fabricated references.

- Chapters 4–8 (Experiment Setup, Results, Persistence Analysis, Evidential Value Discussion, Conclusion) are stubbed, pending experimental data.

# 3. Risk Register

Using the probability/severity framework from the module's own project-management briefing.

| Risk | Probability | Severity | Rating | Mitigation |
| --- | --- | --- | --- | --- |
| Ethics approval delayed or returned with conditions | Probable | Catastrophic (blocks all data collection and marking) | High (12) | Confirm status tomorrow; escalate with supervisor if not yet decided |
| 5-week window insufficient for 3 apps × 13 phases | Probable | Critical | Serious (9) | Get supervisor sign-off tomorrow on scope; consider cutting to 2 apps or a reduced phase set if needed |
| No commercial forensic tool access, narrowing RQ3 | Probable | Marginal (RQ3 still answerable, just narrower) | Serious (6) | Confirm tool access tomorrow; write RQ3 boundary into Methodology now (already done) |
| Wallet app storage assumptions wrong (as already happened once with MetaMask) | Probable | Marginal | Serious (6) | Verify each app's storage backend empirically during the pilot phase before the full run |
| Emulator behaviour diverges from real hardware (Keystore/TEE) | Remote | Marginal | Medium (4) | State as a limitation; consider one physical-device spot-check if time allows |

# 4. Immediate Next Steps

- Take the open items list from the meeting prep notes into tomorrow's meeting and get explicit answers, especially ethics status and scope sign-off.

- Lock the three specific wallet apps and confirm the emulator's root status.

- Start the pilot phase (one wallet through all 13 phases) as soon as ethics approval is confirmed.

- Continue literature reading toward populating Chapter 2, following the thematic structure already drafted.

- File the completed Research Supervision Meeting Notes to Canvas after the meeting, as required by the module.